## Sheet1
[8 empty] | 2020-11-23 | [6 empty] | 2020-11-30 | [6 empty] | 2020-12-07 | [6 empty] | 2020-12-14 | [6 empty] | 2020-12-28 | [6 empty] | 2020-01-04 | [6 empty] | 2021-01-11 | [6 empty] | 2021-01-12
ID | Task | Latest Dependency ID | Assigned To | Progress | Start | End | Difficulty | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S
Website
1 | Visual Layout for Website search page and results page | / |  |  |  |  | 2 | bar: 2020-11-23 M to 2020-11-23 W
2 | Build html, css, and basic js functions for navigation | 1,41 |  |  |  |  | 3 | bar: 2020-11-23 R to 2020-11-30 F
3 | overview search js function(input=query from page, output=list of results from ranking algo) | 2 |  |  |  |  | 2 | bar: 2020-11-30 S to 2020-12-07 M
4 | js function to populate results page with results | 3 |  |  |  |  | 3 | bar: 2020-12-07 T to 2020-12-14 W
5 | test that all elements of website work | 4 |  |  |  |  | 2 | bar: 2020-12-14 R to 2020-12-14 S
Crawler
11 | set up rpi with OS and wired connection to network+internet | / |  |  |  |  | 2 | bar: 2020-11-23 M to 2020-11-23 W
12 | set up ssh and remote desktop | 11 |  |  |  |  | 1 | bar: 2020-11-23 R
13 | write crawler program | 14 |  |  |  |  | 3 | bar: 2020-11-30 S to 2020-12-14 M
14 | write tests | 12 |  |  |  |  | 3 | bar: 2020-11-23 F to 2020-11-30 S
Database
21 | set up rpi with OS, db compatible with Azure and django | 22 |  |  |  |  | 5 | bar: 2020-11-30 W to 2020-12-28 T
22 | determine db strucutre | / |  |  |  |  | 3 | bar: 2020-11-23 M to 2020-11-30 T
23 | implement db structrue | 21 |  |  |  |  | 2 | bar: 2020-12-28 W to 2020-12-28 F
Ranking
31 | research ranking and make diagram of function | / |  |  |  |  | 5 | bar: 2020-11-23 M to 2020-12-07 S
32 | make function(input=query, output=list of results) in python and/or js | 33 |  |  |  |  | 3 | bar: 2020-12-28 W to 2020-01-04 R
33 | write tests | 31 |  |  |  |  | 3 | bar: 2020-12-14 M to 2020-12-28 T
Other
41 | create github repo for group | / |  |  |  |  | 1 | bar: 2020-11-23 M
42 | purchase azure subscription using group account | / |  |  |  |  | 1 | bar: 2020-11-23 M
43 | create webapp resource connected to github repo main branch | 41,42 |  |  |  |  | 1 | bar: 2020-11-23 T
44 | Purchase and configure custom domain | 42 |  |  |  |  | 2 | bar: 2020-11-23 W to 2020-11-23 F